## GanttChart
Travel Diary
| Project Start Date | 2023-12-30 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Business Analyst | Samra Wasim
| Project Lead | Rabia Makkani | [6 empty] | 2023-12-25 | [6 empty] | 2024-01-01 | [6 empty] | 2024-01-08 | [6 empty] | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12
 | time axis 2023-12-25 to 2024-02-18
| TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2023-12-25 to 2024-02-18
1 | PLANNING AND REQUIREMENTS | Rabia Makkani/ Samra Wasim |  | 2023-12-30 | 2023-12-31 | 2 | 100% | 0
2 | UI / UX DESIGN | Maryam Batool |  | 2024-01-01 | 2024-01-03 | 3 | 30% | 3
3 | FRONT-END | Safeer Ahmed / Muhammad Ammar |  | 2024-01-04 | 2024-01-09 | 6 | 0% | 4
4 | BACK-END | Haris Younus/ Aun Muhammad/ |  | 2024-01-10 | 2024-01-19 | 10 | 0% | 8
5 | TESTING | Bushra Ahmed |  | 2024-01-20 | 2024-01-22 | 3 | 0% | 1
6 | MAINTENANCE | All |  | 2024-01-23 | 2024-01-24 | 2 | 0% | 2
Note on B8: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C8: Task Lead Enter the name of the Task Lead in this column.
Note on D8: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E8: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F8: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G8: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H8: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I8: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.